This should be consulted together with Principals Regular Respononsibilities

YEAR PLANNING CALENDAR

| WEEK 1 (15-19 Jan) TERM 1 2-day professional development: whole staff vision alignment, professionalism, teaching strategies, subject head mentoring, induction for new teachers; Subject meetings, vision alignment; SWT team-building; Pastoral care grade meetings; New learner induction programme; Issue extra-mural timetable; Issue extra-lesson/enrichment timetable; Collect all staff signed duty sheets; Grade 1 orientation and information session (learners and parents). NOTE: This should only be done now if it was not done in the previous year. | WEEK 2 Finance meeting; Check new learner data entered; Check admissions register; Staff welcome function with SGB; Join a network/identify a mentor or mentee, as relevant | WEEK 3 SGB meeting - review safety policy; Submit 10th day return; Request profiles | WEEK 4 Monitor attention to culture and climate |
| --- | --- | --- | --- |
| WEEK 5 Staff update on practical information | WEEK 6 Finance meeting; Principal review of delegations | WEEK 7 SGB meeting - review admissions and language policy | WEEK 8 Parent information session; Monitor attention to culture and climate |
| WEEK 9 IQMS DSGs class visit/meeting; Monitor learners’ books and teachers’ subject files; Principal’s review of PGP implementation, effect of leadership style, collaborative efforts, contribution to education community | WEEK 10 Finance meeting; PMDS quarterly; PMDS Annual work plan and signed duty sheets – meet with each support staff member; Develop support staff skills development plan; Collect teachers’ additional work payment claims; Collect teachers’ term reflections | WEEK 11 SGB meeting – review finance policy, review maintenance plan; SGB exec meeting – approve payments and salary review; Open Day | WEEK 12 (28 March) Principal’s reflections – realisation of personal/school vision, role-modelling, relationships, mentoring, successes, fears, challenges, donor interventions, gratitude; SMT term review and next term planning; Issue reports; Analyse performance data (all subjects and discuss improvement strategies and subject SIPS); Parents’ consultation on Term report |
| WEEK 13 (10-13 April) TERM2 Collate annual survey data and submit; | WEEK 14 Finance meeting | WEEK 15 SGB meeting - elect executive, review learner well-being related policies; Order LTSM for following year | WEEK 16 Parent information session; Monitor attention to culture and climate |
| WEEK 17 Moderate exams | WEEK 18 Finance meeting; Principal’s review of delegations; Prepare management of exams booklet | WEEK 19 SGB meeting - approve audited accounts and total amount claimed for Sect 38(A) claims for the following year; Submit audited accounts; Monitor learners’ books and teachers’ subject files | WEEK 20 IQMS DSGs class visit/meeting; Monitor attention to culture and climate; Submit Sect 38(A) applications, if relevant |
| WEEK 21 Repair subject equipment; Principal’s review of PGP implementation, effect of leadership style, collaborative efforts, contribution to education community; PMDS quarterly | WEEK 22 Exams begin grades 1-7; Collect teachers’ additional work payment claims; Collect teachers’ term reflections; Interim assets check | WEEK 23 (22 June) Exams end; SGB meeting - review maintenance plan; SGB exec meeting – approve payments and salary review; SMT term review and next term planning; Principal’s reflections – realisation of personal/school vision, role-modelling, relationships, mentoring, successes, fears, challenges, donor interventions, gratitude Issue reports; Parents’ consultation on Term report | HOLIDAYS |
| WEEK 24 (17-20 July) TERM 3 Analyse performance data (all subjects and principal, discuss improvement strategies and subject SIPS) | WEEK 25 Finance meeting; Conduct IWSE; Review SDP (Develop SDP in SGB election year); Begin SIP | WEEK 26 SGB meeting - approve IWSE and SDP; Grade 9 subject information session (learners and parents); Cost centres submit proposed budgets | WEEK 27 Monitor learners’ books and teachers’ subject files; Complete proposed budget |
| WEEK 28 Finance meeting (draft budget); Principal’s review of delegations; Monitor attention to culture and climate | WEEK 29 SGB meeting - school climate and culture review; Parent information session Alumni function | WEEK 30 IQMS DSGs class visit/meeting; Consult teachers regarding the following year’s duties | WEEK 31 PMDS quarterly; Consult teachers regarding the following year’s duties; SLT duties consultation; Principal’s review of PGP implementation, effect of leadership style, collaborative efforts, contribution to education community |
| WEEK 32 Finance meeting (prepare budget proposal); Collect teachers’ additional work payment claims; Collect teachers’ term reflections; Plan timetable structure; Allocate teachers to teaching classes; Year Plan draft 1; Review General School Information booklet; Review School Agreement form | WEEK 33 SGB meeting (approve proposed budget, review disciplinary policy and code of conduct); SGB exec meeting– approve payments and salary review; SMT term review and next term planning | WEEK 34 (28 Sept) Issue reports; Parents’ consultation on Term report; Analyse performance data (all subjects and discuss improvement strategies and subject improvement plans; Principal’s reflections – realisation of personal/school vision, role-modelling, relationships, mentoring, successes, fears, challenges, donor interventions, gratitude | HOLIDAYS ICT upgrading if necessary |
| WEEK 35 (9 Oct) TERM 4 RCL/ Prefect training; RCL/ Prefect induction; Prepare end-of-year procedures booklet | WEEK 36 Finance meeting (prepare for AGM/Budget meeting); AGM/Budget meeting; Grade 1 (following year) information evening | WEEK 37 SGB meeting; Year Plan draft 2; Timetable draft 1; Staff submit stationery orders; Moderate exam papers; Principal’s review of PGP implementation, effect of leadership style, collaborative efforts, contribution to education community | WEEK 38 Monitor learners’ books and teachers’ subject files; Collect teachers’ additional work payment claims; Collect teachers’ term reflections; Grade 7 farewell awards; Prepare beginning-of-year booklet |
| WEEK 39 Finance meeting; IQMS DSGs class visit/meeting and summative scoring completed; Collect all IQMS materials; SDT IQMS moderation meeting; Prepare staff information booklet; Order stationery | WEEK 40 SGB meeting/function; PMDS quarterly; Prepare administration information booklet; Staff consultations begin; Review policy register and check updates; Update honours board | WEEK 41 SGB exec meeting– approve payments and salary review; Prepare contracts/letters of appointment for SGB staff; Staff consultations; Confirm all leadership/ management roles; Year plan final; Extra mural timetable draft 1; Complete school SBA schedule for following year; Submit IQMS scores; | WEEK 42 Prepare school PDP; Prepare school improvement plan (SIP); Finalise timetable for printing; Print and issue timetables; Compile composite timetable; Sign off SACE CPTD points for teachers and submit Principal’s one; Complete staff consultations; Complete stock-takes/asset register check |
| WEEK 43 Hold promotions meetings for each grade; Finance meeting; Check affiliation fees have been paid for the following year (or prepare the payment schedule for payment in January); Submit promotion schedules | WEEK 44 (10-14 Dec) Issue reports; Issue school magazine, if relevant; New staff orientation afternoon; Teachers submit signed duty sheets for the following year; Review principal’s vision for self and school for action where relevant | HOLIDAYS | HOLIDAYS Week before school opens Clean grounds and buildings; SMT term review, including analysis of results, and planning review; Meet with new teachers |